## Slide 1
INTERNATIONAL SEMINAR
Mock Drill Plan
A practical rehearsal roadmap for smooth stage, guest, technical and certificate coordination
Baikuntha College of Education | Internal Quality Assurance Cell (IQAC)
Recommended duration: 60–75 minutes
Best time: Seminar-এর আগের দিন / previous day
FINAL REHEARSAL
Run the event before the event

## Slide 2
BAIKUNTHA COLLEGE OF EDUCATION | IQAC
International Seminar Mock Drill
Why Mock Drill is Needed
Objective: reduce delay, confusion and protocol mistakes on the seminar day
Prepared for internal rehearsal and coordination
⏱
Time Discipline
Every transition has a target time and a responsible person.
🎙
Stage Confidence
Anchor, mic team and speakers know the exact movement flow.
🤝
Guest Protocol
Reception, escorting, seating and felicitation are rehearsed in advance.
💻
Technical Readiness
Laptop, projector, online link, mic and backup systems are checked.
📜
Certificate Flow
Distribution is arranged to avoid crowding and delay.
📸
Photo Control
Official shots are planned so the stage does not become crowded.
Core message to Principal: A 60–75 minute rehearsal will make the seminar look professional, punctual and international-standard.

## Slide 3
BAIKUNTHA COLLEGE OF EDUCATION | IQAC
International Seminar Mock Drill
Mock Drill Team Structure
Assign one responsible person for each flow before rehearsal starts
Prepared for internal rehearsal and coordination
Overall Coordinator
Runs the rehearsal and final review
Anchor / MC
Practices stage script and transitions
Guest Liaison
Receives and escorts dignitaries
Stage Manager
Controls dais, lamp, bouquet and mic movement
Technical Lead
Checks projector, laptop, online link and audio
Time Keeper
Shows 5 min / 2 min / conclude cards
Certificate Team
Arranges certificates category-wise / alphabetical
Photography Lead
Follows official shot list
Rule: No volunteer leaves assigned position without informing the coordinator.

## Slide 4
BAIKUNTHA COLLEGE OF EDUCATION | IQAC
International Seminar Mock Drill
60–75 Minute Mock Drill Flow
Rehearse the actual programme movement in fast-forward mode
Prepared for internal rehearsal and coordination
1
Assembly & Role Confirmation
5 min
2
Guest Arrival & Reception
5 min
3
Anchor Opening
5 min
4
Lamp Lighting + Music
7 min
5
Welcome + Introductory Address
5 min
6
Felicitation Drill
7 min
7
Keynote / International Lecture Transition
5 min
8
Q&A + Lunch Transition
8 min
9
Technical + Certificate + Valedictory
20 min
10
Final Review
10 min
Fast-forward rehearsal means: each real segment is practiced only enough to confirm movement, mic, cue and responsibility.

## Slide 5
BAIKUNTHA COLLEGE OF EDUCATION | IQAC
International Seminar Mock Drill
Protocol Drill 1: Guest Arrival & Stage Opening
Practice dignity, sequence and movement—not long speeches
Prepared for internal rehearsal and coordination
Reception Checklist
✓ Gate / reception desk welcomes guests
✓ Badge, seminar kit and seating assistance
✓ Guest liaison escorts VIPs to reserved area
✓ Anchor checks final names and designations
✓ Mic, podium and lamp area checked before start
Anchor Opening Cue
“Good morning, respected dignitaries, distinguished resource persons, principals, faculty members, research scholars, student-teachers and participants. On behalf of Baikuntha College of Education and IQAC, I warmly welcome you all to this International Seminar.”
Rehearse once with actual microphone and actual stage position.

## Slide 6
BAIKUNTHA COLLEGE OF EDUCATION | IQAC
International Seminar Mock Drill
Protocol Drill 2: Lamp Lighting, Felicitation & Speeches
Pre-decide who moves, who presents, who photographs, and who speaks
Prepared for internal rehearsal and coordination
Lamp Lighting
Anchor cue → Escort guests → Light lamp → Music → Photo → Return to seats
Target: 5–7 min
Felicitation
Guest name → Presenter assigned → Item ready → Photo → Next guest
Avoid crowding on stage
Brief Addresses
Only selected speakers; request concise remarks before inviting
Protect Keynote time
Key instruction: Do not invite too many people to the stage at the same time.

## Slide 7
BAIKUNTHA COLLEGE OF EDUCATION | IQAC
International Seminar Mock Drill
Academic Session Drill
Moderator, time keeper and technical team must work together
Prepared for internal rehearsal and coordination
Keynote Address
Speaker introduction should be 2–3 lines only. Full CV should not be read.
International Invited Lecture
Confirm online/hybrid link, backup laptop, mic and screen-sharing.
Invited Addresses
Use speaker time cards: 5 min, 2 min, Please conclude.
Q&A Protocol
Question: max 1 minute; Answer: 2–3 minutes; name + institution first.
Academic discipline = international quality

## Slide 8
BAIKUNTHA COLLEGE OF EDUCATION | IQAC
International Seminar Mock Drill
Technical Session, Certificate & Photo Drill
Avoid last-hour chaos by rehearsing movements
Prepared for internal rehearsal and coordination
Technical Session
Chairpersons seated → Presenter called → PPT loaded → Time card → Chairperson comment
Certificate Distribution
Certificates arranged → Name called → Handover → Photo → Exit opposite side
Group Photo
Front row VIPs → Second row resource persons → Back rows faculty / participants
Stage movement rule: One entry side and one exit side should be fixed for certificate flow.

## Slide 9
BAIKUNTHA COLLEGE OF EDUCATION | IQAC
International Seminar Mock Drill
Emergency Backup Kit
Keep these ready before the rehearsal and on the seminar day
Prepared for internal rehearsal and coordination
Audio
2 microphones + 1 backup
Display
Projector, HDMI, clicker, backup laptop
Connectivity
Wi-Fi + mobile hotspot + online meeting link
Power
Extension board + chargers
Documents
Printed schedule + anchor script + guest list
Participant Support
Badges, certificates, first-aid, water
Backup principle: If one device fails, the programme should continue within 2 minutes.

## Slide 10
BAIKUNTHA COLLEGE OF EDUCATION | IQAC
International Seminar Mock Drill
Final 10-Minute Review After Mock Drill
Only six points should be reviewed—short, sharp and action-oriented
Prepared for internal rehearsal and coordination
1. Timing
2. Guest Movement
3. Anchor Cues
4. Microphone
5. Presentation System
6. Photography
Principal’s decision needed: Approve one full mock drill and assign final coordinators today.